## Inputs
Start Date |  |  | 2021-02-02 07:00 | DateTimeStart
Gantt Chart Periodicity |  |  | 0.5 | ChartPeridicity
| type |  | mins | ChartPeriodicityType
Can Start After
Items |  |  | Item |  | Item One | Item two
| Wake Up |  | Wake Up
| Start Coffee Maker |  | Start Coffee Maker |  | Wake Up
| Have Shower |  | Have Shower |  | Start Coffee Maker
| Get Dressed |  | Get Dressed |  | Have Shower
| Make Toast |  | Make Toast |  | Get Dressed
| Pour Coffee |  | Pour Coffee |  | Get Dressed
| Add Milk |  | Add Milk |  | Pour Coffee
| Eat Breakfast |  | Eat Breakfast |  | Make Toast | Add Milk
| Watch News |  | Watch News |  | Get Dressed
| Begin Work |  | Begin Work |  | Watch News | Eat Breakfast
| Make Dinner |  | Make Dinner |  | Begin Work
| Eat Dinner |  | Eat Dinner |  | Make Dinner
| Create Gantt Chart |  | Create Gantt Chart |  | Eat Dinner
| Sleep |  | Sleep |  | Create Gantt Chart
|  |  |  | Tasks |  |  | TasksMap
Time types |  |  | months | weeks | days | hours | mins | TimeTypes
| mins in type | min/type | 43200 | 10080 | 1440 | 60 | 1 | TimeTypes_Converter
Time Taken |  |  | type | amount
| Wake Up |  | mins | 15
| Start Coffee Maker |  | mins | 5
| Have Shower |  | mins | 10
| Get Dressed |  | mins | 5
| Make Toast |  | mins | 5
| Pour Coffee |  | mins | 2
| Add Milk |  | mins | 0.5
| Eat Breakfast |  | mins | 25
| Watch News |  | hours | 1
| Begin Work |  | hours | 8
| Make Dinner |  | hours | 0.5
| Eat Dinner |  | mins | 30
| Create Gantt Chart |  | hours | 1
| Sleep |  | hours | 7
|  |  | TimeTaken_Type | TimeTaken_Amount

## Calculations
Static
Timing |  | Converter | Start | End
| Wake Up | 1 | 2021-02-02 07:00 | 2021-02-02 07:15
| Start Coffee Maker | 1 | 2021-02-02 07:15 | 2021-02-02 07:20
| Have Shower | 1 | 2021-02-02 07:20 | 2021-02-02 07:30
| Get Dressed | 1 | 2021-02-02 07:30 | 2021-02-02 07:35
| Make Toast | 1 | 2021-02-02 07:35 | 2021-02-02 07:40
| Pour Coffee | 1 | 2021-02-02 07:35 | 2021-02-02 07:37
| Add Milk | 1 | 2021-02-02 07:37 | 2021-02-02 07:37
| Eat Breakfast | 1 | 2021-02-02 07:40 | 2021-02-02 08:05
| Watch News | 60 | 2021-02-02 07:35 | 2021-02-02 08:35
| Begin Work | 60 | 2021-02-02 08:35 | 2021-02-02 16:35
| Make Dinner | 60 | 2021-02-02 16:35 | 2021-02-02 17:05
| Eat Dinner | 1 | 2021-02-02 17:05 | 2021-02-02 17:35
| Create Gantt Chart | 60 | 2021-02-02 17:35 | 2021-02-02 18:35
| Sleep | 60 | 2021-02-02 18:35 | 2021-02-03 01:35
|  |  | TimeStart | TimeEnd
Timeline
Periods |  | 44229.2917 | 44229.292 | 44229.2924 | 44229.2927 | 44229.2931 | 44229.2934 | 44229.2938 | 44229.2941 | 44229.2944 | 44229.2948 | 44229.2951 | 44229.2955 | 44229.2958 | 44229.2962 | 44229.2965 | 44229.2969 | 44229.2972 | 44229.2976 | 44229.2979 | 44229.2983 | 44229.2986 | 44229.299 | 44229.2993 | 44229.2997 | 44229.3 | 44229.3003 | 44229.3007 | 44229.301 | 44229.3014 | 44229.3017 | 44229.3021 | 44229.3024 | 44229.3028 | 44229.3031 | 44229.3035 | 44229.3038 | 44229.3042 | 44229.3045 | 44229.3049 | 44229.3052 | 44229.3056 | 44229.3059 | 44229.3063 | 44229.3066 | 44229.3069 | 44229.3073 | 44229.3076 | 44229.308 | 44229.3083 | 44229.3087 | 44229.309 | 44229.3094 | 44229.3097 | 44229.3101 | 44229.3104 | 44229.3108 | 44229.3111 | 44229.3115 | 44229.3118 | 44229.3122 | 44229.3125 | 44229.3128 | 44229.3132 | 44229.3135 | 44229.3139 | 44229.3142 | 44229.3146 | 44229.3149 | 44229.3153 | 44229.3156 | 44229.316 | 44229.3163 | 44229.3167 | 44229.317 | 44229.3174 | 44229.3177 | 44229.3181 | 44229.3184 | 44229.3188 | 44229.3191 | 44229.3194 | 44229.3198 | 44229.3201 | 44229.3205 | 44229.3208 | 44229.3212 | 44229.3215 | 44229.3219 | 44229.3222 | 44229.3226 | 44229.3229 | 44229.3233 | 44229.3236 | 44229.324 | 44229.3243 | 44229.3247 | 44229.325 | 44229.3253 | 44229.3257 | 44229.326 | 44229.3264 | 44229.3267 | 44229.3271 | 44229.3274 | 44229.3278 | 44229.3281 | 44229.3285 | 44229.3288 | 44229.3292 | 44229.3295 | 44229.3299 | 44229.3302 | 44229.3306 | 44229.3309 | 44229.3313 | 44229.3316 | 44229.3319 | 44229.3323 | 44229.3326 | 44229.333 | 44229.3333 | 44229.3337 | 44229.334 | 44229.3344 | 44229.3347 | 44229.3351 | 44229.3354 | 44229.3358 | 44229.3361 | 44229.3365 | 44229.3368 | 44229.3372 | 44229.3375 | 44229.3378 | 44229.3382 | 44229.3385 | 44229.3389 | 44229.3392 | 44229.3396 | 44229.3399 | 44229.3403 | 44229.3406 | 44229.341 | 44229.3413 | 44229.3417 | 44229.342 | 44229.3424 | 44229.3427 | 44229.3431 | 44229.3434 | 44229.3438 | 44229.3441 | 44229.3444 | 44229.3448 | 44229.3451 | 44229.3455 | 44229.3458 | 44229.3462 | 44229.3465 | 44229.3469 | 44229.3472 | 44229.3476 | 44229.3479 | 44229.3483 | 44229.3486 | 44229.349 | 44229.3493 | 44229.3497 | 44229.35 | 44229.3503 | 44229.3507 | 44229.351 | 44229.3514 | 44229.3517 | 44229.3521 | 44229.3524 | 44229.3528 | 44229.3531 | 44229.3535 | 44229.3538 | 44229.3542 | 44229.3545 | 44229.3549 | 44229.3552 | 44229.3556 | 44229.3559 | 44229.3563 | 44229.3566 | 44229.3569 | 44229.3573 | 44229.3576 | 44229.358 | 44229.3583 | 44229.3587 | 44229.359 | 44229.3594 | 44229.3597 | 44229.3601 | 44229.3604 | 44229.3608 | 44229.3611 | 44229.3615 | 44229.3618 | 44229.3622 | 44229.3625 | 44229.3628 | 44229.3632 | 44229.3635 | 44229.3639 | 44229.3642 | 44229.3646 | 44229.3649 | 44229.3653 | 44229.3656 | 44229.366 | 44229.3663 | 44229.3667 | 44229.367 | 44229.3674 | 44229.3677 | 44229.3681 | 44229.3684 | 44229.3688 | 44229.3691 | 44229.3694 | 44229.3698 | 44229.3701 | 44229.3705 | 44229.3708 | 44229.3712 | 44229.3715 | 44229.3719 | 44229.3722 | 44229.3726 | 44229.3729 | 44229.3733 | 44229.3736 | 44229.374 | 44229.3743 | 44229.3747 | 44229.375 | 44229.3753 | 44229.3757 | 44229.376 | 44229.3764 | 44229.3767 | 44229.3771 | 44229.3774 | 44229.3778 | 44229.3781 | 44229.3785 | 44229.3788 | 44229.3792 | 44229.3795 | 44229.3799 | 44229.3802 | 44229.3806 | 44229.3809 | 44229.3813 | 44229.3816 | 44229.3819 | 44229.3823 | 44229.3826 | 44229.383 | 44229.3833 | 44229.3837 | 44229.384 | 44229.3844 | 44229.3847 | 44229.3851 | 44229.3854 | 44229.3858 | 44229.3861 | 44229.3865 | 44229.3868 | 44229.3872 | 44229.3875 | 44229.3878 | 44229.3882 | 44229.3885 | 44229.3889 | 44229.3892 | 44229.3896 | 44229.3899 | 44229.3903 | 44229.3906 | 44229.391 | 44229.3913 | 44229.3917 | 44229.392 | 44229.3924 | 44229.3927 | 44229.3931 | 44229.3934 | 44229.3938 | 44229.3941 | 44229.3944 | 44229.3948 | 44229.3951 | 44229.3955 | 44229.3958 | 44229.3962 | 44229.3965 | 44229.3969 | 44229.3972 | 44229.3976 | 44229.3979 | 44229.3983 | 44229.3986 | 44229.399 | 44229.3993 | 44229.3997 | 44229.4 | 44229.4003 | 44229.4007 | 44229.401 | 44229.4014 | 44229.4017 | 44229.4021 | 44229.4024 | 44229.4028 | 44229.4031 | 44229.4035 | 44229.4038 | 44229.4042 | 44229.4045 | 44229.4049 | 44229.4052 | 44229.4056 | 44229.4059 | 44229.4063 | 44229.4066 | 44229.4069 | 44229.4073 | 44229.4076 | 44229.408 | 44229.4083 | 44229.4087 | 44229.409 | 44229.4094 | 44229.4097 | 44229.4101 | 44229.4104 | 44229.4108 | 44229.4111 | 44229.4115 | 44229.4118 | 44229.4122 | 44229.4125 | 44229.4128 | 44229.4132 | 44229.4135 | 44229.4139 | 44229.4142 | 44229.4146 | 44229.4149 | 44229.4153 | 44229.4156 | 44229.416 | 44229.4163 | 44229.4167 | 44229.417 | 44229.4174 | 44229.4177 | 44229.4181 | 44229.4184 | 44229.4188 | 44229.4191 | 44229.4194 | 44229.4198 | 44229.4201 | 44229.4205 | 44229.4208 | 44229.4212 | 44229.4215 | 44229.4219 | 44229.4222 | 44229.4226 | 44229.4229 | 44229.4233 | 44229.4236 | 44229.424 | 44229.4243 | 44229.4247 | 44229.425 | 44229.4253 | 44229.4257 | 44229.426 | 44229.4264 | 44229.4267 | 44229.4271 | 44229.4274 | 44229.4278 | 44229.4281 | 44229.4285 | 44229.4288 | 44229.4292 | 44229.4295 | 44229.4299 | 44229.4302 | 44229.4306 | 44229.4309 | 44229.4313 | 44229.4316 | 44229.4319 | 44229.4323 | 44229.4326 | 44229.433 | 44229.4333 | 44229.4337 | 44229.434 | 44229.4344 | 44229.4347 | 44229.4351 | 44229.4354 | 44229.4358 | 44229.4361 | 44229.4365 | 44229.4368 | 44229.4372 | 44229.4375 | 44229.4378 | 44229.4382 | 44229.4385 | 44229.4389 | 44229.4392 | 44229.4396 | 44229.4399 | 44229.4403 | 44229.4406 | 44229.441 | 44229.4413 | 44229.4417 | 44229.442 | 44229.4424 | 44229.4427 | 44229.4431 | 44229.4434 | 44229.4438 | 44229.4441 | 44229.4444 | 44229.4448 | 44229.4451 | 44229.4455 | 44229.4458 | 44229.4462 | 44229.4465 | 44229.4469 | 44229.4472 | 44229.4476 | 44229.4479 | 44229.4483 | 44229.4486 | 44229.449 | 44229.4493 | 44229.4497 | 44229.45 | 44229.4503 | 44229.4507 | 44229.451 | 44229.4514 | 44229.4517 | 44229.4521 | 44229.4524 | 44229.4528 | 44229.4531 | 44229.4535 | 44229.4538 | 44229.4542 | 44229.4545 | 44229.4549 | 44229.4552 | 44229.4556 | 44229.4559 | 44229.4563 | 44229.4566 | 44229.4569 | 44229.4573 | 44229.4576 | 44229.458 | 44229.4583 | 44229.4587 | 44229.459 | 44229.4594 | 44229.4597 | 44229.4601 | 44229.4604 | 44229.4608 | 44229.4611 | 44229.4615 | 44229.4618 | 44229.4622 | 44229.4625 | 44229.4628 | 44229.4632 | 44229.4635 | 44229.4639 | 44229.4642 | 44229.4646 | 44229.4649 | 44229.4653 | 44229.4656 | 44229.466 | 44229.4663 | 44229.4667 | 44229.467 | 44229.4674 | 44229.4677 | 44229.4681 | 44229.4684 | 44229.4688 | 44229.4691 | 44229.4694 | 44229.4698 | 44229.4701 | 44229.4705 | 44229.4708 | 44229.4712 | 44229.4715 | 44229.4719 | 44229.4722 | 44229.4726 | 44229.4729 | 44229.4733 | 44229.4736 | 44229.474 | 44229.4743 | 44229.4747 | 44229.475 | 44229.4753 | 44229.4757 | 44229.476 | 44229.4764 | 44229.4767 | 44229.4771 | 44229.4774 | 44229.4778 | 44229.4781 | 44229.4785 | 44229.4788 | 44229.4792 | 44229.4795 | 44229.4799 | 44229.4802 | 44229.4806 | 44229.4809 | 44229.4813 | 44229.4816 | 44229.4819 | 44229.4823 | 44229.4826 | 44229.483 | 44229.4833 | 44229.4837 | 44229.484 | 44229.4844 | 44229.4847 | 44229.4851 | 44229.4854 | 44229.4858 | 44229.4861 | 44229.4865 | 44229.4868 | 44229.4872 | 44229.4875 | 44229.4878 | 44229.4882 | 44229.4885 | 44229.4889 | 44229.4892 | 44229.4896 | 44229.4899 | 44229.4903 | 44229.4906 | 44229.491 | 44229.4913 | 44229.4917 | 44229.492 | 44229.4924 | 44229.4927 | 44229.4931 | 44229.4934 | 44229.4938 | 44229.4941 | 44229.4944 | 44229.4948 | 44229.4951 | 44229.4955 | 44229.4958 | 44229.4962 | 44229.4965 | 44229.4969 | 44229.4972 | 44229.4976 | 44229.4979 | 44229.4983 | 44229.4986 | 44229.499 | 44229.4993 | 44229.4997 | 44229.5 | 44229.5003 | 44229.5007 | 44229.501 | 44229.5014 | 44229.5017 | 44229.5021 | 44229.5024 | 44229.5028 | 44229.5031 | 44229.5035 | 44229.5038 | 44229.5042 | 44229.5045 | 44229.5049 | 44229.5052 | 44229.5056 | 44229.5059 | 44229.5063 | 44229.5066 | 44229.5069 | 44229.5073 | 44229.5076 | 44229.508 | 44229.5083 | 44229.5087 | 44229.509 | 44229.5094 | 44229.5097 | 44229.5101 | 44229.5104 | 44229.5108 | 44229.5111 | 44229.5115 | 44229.5118 | 44229.5122 | 44229.5125 | 44229.5128 | 44229.5132 | 44229.5135 | 44229.5139 | 44229.5142 | 44229.5146 | 44229.5149 | 44229.5153 | 44229.5156 | 44229.516 | 44229.5163 | 44229.5167 | 44229.517 | 44229.5174 | 44229.5177 | 44229.5181 | 44229.5184 | 44229.5188 | 44229.5191 | 44229.5194 | 44229.5198 | 44229.5201 | 44229.5205 | 44229.5208 | 44229.5212 | 44229.5215 | 44229.5219 | 44229.5222 | 44229.5226 | 44229.5229 | 44229.5233 | 44229.5236 | 44229.524 | 44229.5243 | 44229.5247 | 44229.525 | 44229.5253 | 44229.5257 | 44229.526 | 44229.5264 | 44229.5267 | 44229.5271 | 44229.5274 | 44229.5278 | 44229.5281 | 44229.5285 | 44229.5288 | 44229.5292 | 44229.5295 | 44229.5299 | 44229.5302 | 44229.5306 | 44229.5309 | 44229.5313 | 44229.5316 | 44229.5319 | 44229.5323 | 44229.5326 | 44229.533 | Timeline
Formulas:
Start = MAX(IF(INDEX(TasksMap,MATCH(B13,Tasks,0),)=B12:B12,H12:[End, row above]))
End = [Start]+[Converter]*INDEX(TimeTaken_Amount,MATCH(B12,Tasks,0))/MinsInDay

## Display
Task |  | Start | Finish | 44229.2917 | 44229.292 | 44229.2924 | 44229.2927 | 44229.2931 | 44229.2934 | 44229.2938 | 44229.2941 | 44229.2944 | 44229.2948 | 44229.2951 | 44229.2955 | 44229.2958 | 44229.2962 | 44229.2965 | 44229.2969 | 44229.2972 | 44229.2976 | 44229.2979 | 44229.2983 | 44229.2986 | 44229.299 | 44229.2993 | 44229.2997 | 44229.3 | 44229.3003 | 44229.3007 | 44229.301 | 44229.3014 | 44229.3017 | 44229.3021 | 44229.3024 | 44229.3028 | 44229.3031 | 44229.3035 | 44229.3038 | 44229.3042 | 44229.3045 | 44229.3049 | 44229.3052 | 44229.3056 | 44229.3059 | 44229.3063 | 44229.3066 | 44229.3069 | 44229.3073 | 44229.3076 | 44229.308 | 44229.3083 | 44229.3087 | 44229.309 | 44229.3094 | 44229.3097 | 44229.3101 | 44229.3104 | 44229.3108 | 44229.3111 | 44229.3115 | 44229.3118 | 44229.3122 | 44229.3125 | 44229.3128 | 44229.3132 | 44229.3135 | 44229.3139 | 44229.3142 | 44229.3146 | 44229.3149 | 44229.3153 | 44229.3156 | 44229.316 | 44229.3163 | 44229.3167 | 44229.317 | 44229.3174 | 44229.3177 | 44229.3181 | 44229.3184 | 44229.3188 | 44229.3191 | 44229.3194 | 44229.3198 | 44229.3201 | 44229.3205 | 44229.3208 | 44229.3212 | 44229.3215 | 44229.3219 | 44229.3222 | 44229.3226 | 44229.3229 | 44229.3233 | 44229.3236 | 44229.324 | 44229.3243 | 44229.3247 | 44229.325 | 44229.3253 | 44229.3257 | 44229.326 | 44229.3264 | 44229.3267 | 44229.3271 | 44229.3274 | 44229.3278 | 44229.3281 | 44229.3285 | 44229.3288 | 44229.3292 | 44229.3295 | 44229.3299 | 44229.3302 | 44229.3306 | 44229.3309 | 44229.3313 | 44229.3316 | 44229.3319 | 44229.3323 | 44229.3326 | 44229.333 | 44229.3333 | 44229.3337 | 44229.334 | 44229.3344 | 44229.3347 | 44229.3351 | 44229.3354 | 44229.3358 | 44229.3361 | 44229.3365 | 44229.3368 | 44229.3372 | 44229.3375 | 44229.3378 | 44229.3382 | 44229.3385 | 44229.3389 | 44229.3392 | 44229.3396 | 44229.3399 | 44229.3403 | 44229.3406 | 44229.341 | 44229.3413 | 44229.3417 | 44229.342 | 44229.3424 | 44229.3427 | 44229.3431 | 44229.3434 | 44229.3438 | 44229.3441 | 44229.3444 | 44229.3448 | 44229.3451 | 44229.3455 | 44229.3458 | 44229.3462 | 44229.3465 | 44229.3469 | 44229.3472 | 44229.3476 | 44229.3479 | 44229.3483 | 44229.3486 | 44229.349 | 44229.3493 | 44229.3497 | 44229.35 | 44229.3503 | 44229.3507 | 44229.351 | 44229.3514 | 44229.3517 | 44229.3521 | 44229.3524 | 44229.3528 | 44229.3531 | 44229.3535 | 44229.3538 | 44229.3542 | 44229.3545 | 44229.3549 | 44229.3552 | 44229.3556 | 44229.3559 | 44229.3563 | 44229.3566 | 44229.3569 | 44229.3573 | 44229.3576 | 44229.358 | 44229.3583 | 44229.3587 | 44229.359 | 44229.3594 | 44229.3597 | 44229.3601 | 44229.3604 | 44229.3608 | 44229.3611 | 44229.3615 | 44229.3618 | 44229.3622 | 44229.3625 | 44229.3628 | 44229.3632 | 44229.3635 | 44229.3639 | 44229.3642 | 44229.3646 | 44229.3649 | 44229.3653 | 44229.3656 | 44229.366 | 44229.3663 | 44229.3667 | 44229.367 | 44229.3674 | 44229.3677 | 44229.3681 | 44229.3684 | 44229.3688 | 44229.3691 | 44229.3694 | 44229.3698 | 44229.3701 | 44229.3705 | 44229.3708 | 44229.3712 | 44229.3715 | 44229.3719 | 44229.3722 | 44229.3726 | 44229.3729 | 44229.3733 | 44229.3736 | 44229.374 | 44229.3743 | 44229.3747 | 44229.375 | 44229.3753 | 44229.3757 | 44229.376 | 44229.3764 | 44229.3767 | 44229.3771 | 44229.3774 | 44229.3778 | 44229.3781 | 44229.3785 | 44229.3788 | 44229.3792 | 44229.3795 | 44229.3799 | 44229.3802 | 44229.3806 | 44229.3809 | 44229.3813 | 44229.3816 | 44229.3819 | 44229.3823 | 44229.3826 | 44229.383 | 44229.3833 | 44229.3837 | 44229.384 | 44229.3844 | 44229.3847 | 44229.3851 | 44229.3854 | 44229.3858 | 44229.3861 | 44229.3865 | 44229.3868 | 44229.3872 | 44229.3875 | 44229.3878 | 44229.3882 | 44229.3885 | 44229.3889 | 44229.3892 | 44229.3896 | 44229.3899 | 44229.3903 | 44229.3906 | 44229.391 | 44229.3913 | 44229.3917 | 44229.392 | 44229.3924 | 44229.3927 | 44229.3931 | 44229.3934 | 44229.3938 | 44229.3941 | 44229.3944 | 44229.3948 | 44229.3951 | 44229.3955 | 44229.3958 | 44229.3962 | 44229.3965 | 44229.3969 | 44229.3972 | 44229.3976 | 44229.3979 | 44229.3983 | 44229.3986 | 44229.399 | 44229.3993 | 44229.3997 | 44229.4 | 44229.4003 | 44229.4007 | 44229.401 | 44229.4014 | 44229.4017 | 44229.4021 | 44229.4024 | 44229.4028 | 44229.4031 | 44229.4035 | 44229.4038 | 44229.4042 | 44229.4045 | 44229.4049 | 44229.4052 | 44229.4056 | 44229.4059 | 44229.4063 | 44229.4066 | 44229.4069 | 44229.4073 | 44229.4076 | 44229.408 | 44229.4083 | 44229.4087 | 44229.409 | 44229.4094 | 44229.4097 | 44229.4101 | 44229.4104 | 44229.4108 | 44229.4111 | 44229.4115 | 44229.4118 | 44229.4122 | 44229.4125 | 44229.4128 | 44229.4132 | 44229.4135 | 44229.4139 | 44229.4142 | 44229.4146 | 44229.4149 | 44229.4153 | 44229.4156 | 44229.416 | 44229.4163 | 44229.4167 | 44229.417 | 44229.4174 | 44229.4177 | 44229.4181 | 44229.4184 | 44229.4188 | 44229.4191 | 44229.4194 | 44229.4198 | 44229.4201 | 44229.4205 | 44229.4208 | 44229.4212 | 44229.4215 | 44229.4219 | 44229.4222 | 44229.4226 | 44229.4229 | 44229.4233 | 44229.4236 | 44229.424 | 44229.4243 | 44229.4247 | 44229.425 | 44229.4253 | 44229.4257 | 44229.426 | 44229.4264 | 44229.4267 | 44229.4271 | 44229.4274 | 44229.4278 | 44229.4281 | 44229.4285 | 44229.4288 | 44229.4292 | 44229.4295 | 44229.4299 | 44229.4302 | 44229.4306 | 44229.4309 | 44229.4313 | 44229.4316 | 44229.4319 | 44229.4323 | 44229.4326 | 44229.433 | 44229.4333 | 44229.4337 | 44229.434 | 44229.4344 | 44229.4347 | 44229.4351 | 44229.4354 | 44229.4358 | 44229.4361 | 44229.4365 | 44229.4368 | 44229.4372 | 44229.4375 | 44229.4378 | 44229.4382 | 44229.4385 | 44229.4389 | 44229.4392 | 44229.4396 | 44229.4399 | 44229.4403 | 44229.4406 | 44229.441 | 44229.4413 | 44229.4417 | 44229.442 | 44229.4424 | 44229.4427 | 44229.4431 | 44229.4434 | 44229.4438 | 44229.4441 | 44229.4444 | 44229.4448 | 44229.4451 | 44229.4455 | 44229.4458 | 44229.4462 | 44229.4465 | 44229.4469 | 44229.4472 | 44229.4476 | 44229.4479 | 44229.4483 | 44229.4486 | 44229.449 | 44229.4493 | 44229.4497 | 44229.45 | 44229.4503 | 44229.4507 | 44229.451 | 44229.4514 | 44229.4517 | 44229.4521 | 44229.4524 | 44229.4528 | 44229.4531 | 44229.4535 | 44229.4538 | 44229.4542 | 44229.4545 | 44229.4549 | 44229.4552 | 44229.4556 | 44229.4559 | 44229.4563 | 44229.4566 | 44229.4569 | 44229.4573 | 44229.4576 | 44229.458 | 44229.4583 | 44229.4587 | 44229.459 | 44229.4594 | 44229.4597 | 44229.4601 | 44229.4604 | 44229.4608 | 44229.4611 | 44229.4615 | 44229.4618 | 44229.4622 | 44229.4625 | 44229.4628 | 44229.4632 | 44229.4635 | 44229.4639 | 44229.4642 | 44229.4646 | 44229.4649 | 44229.4653 | 44229.4656 | 44229.466 | 44229.4663 | 44229.4667 | 44229.467 | 44229.4674 | 44229.4677 | 44229.4681 | 44229.4684 | 44229.4688 | 44229.4691 | 44229.4694 | 44229.4698 | 44229.4701 | 44229.4705 | 44229.4708 | 44229.4712 | 44229.4715 | 44229.4719 | 44229.4722 | 44229.4726 | 44229.4729 | 44229.4733 | 44229.4736 | 44229.474 | 44229.4743 | 44229.4747 | 44229.475 | 44229.4753 | 44229.4757 | 44229.476 | 44229.4764 | 44229.4767 | 44229.4771 | 44229.4774 | 44229.4778 | 44229.4781 | 44229.4785 | 44229.4788 | 44229.4792 | 44229.4795 | 44229.4799 | 44229.4802 | 44229.4806 | 44229.4809 | 44229.4813 | 44229.4816 | 44229.4819 | 44229.4823 | 44229.4826 | 44229.483 | 44229.4833 | 44229.4837 | 44229.484 | 44229.4844 | 44229.4847 | 44229.4851 | 44229.4854 | 44229.4858 | 44229.4861 | 44229.4865 | 44229.4868 | 44229.4872 | 44229.4875 | 44229.4878 | 44229.4882 | 44229.4885 | 44229.4889 | 44229.4892 | 44229.4896 | 44229.4899 | 44229.4903 | 44229.4906 | 44229.491 | 44229.4913 | 44229.4917 | 44229.492 | 44229.4924 | 44229.4927 | 44229.4931 | 44229.4934 | 44229.4938 | 44229.4941 | 44229.4944 | 44229.4948 | 44229.4951 | 44229.4955 | 44229.4958 | 44229.4962 | 44229.4965 | 44229.4969 | 44229.4972 | 44229.4976 | 44229.4979 | 44229.4983 | 44229.4986 | 44229.499 | 44229.4993 | 44229.4997 | 44229.5 | 44229.5003 | 44229.5007 | 44229.501 | 44229.5014 | 44229.5017 | 44229.5021 | 44229.5024 | 44229.5028 | 44229.5031 | 44229.5035 | 44229.5038 | 44229.5042 | 44229.5045 | 44229.5049 | 44229.5052 | 44229.5056 | 44229.5059 | 44229.5063 | 44229.5066 | 44229.5069 | 44229.5073 | 44229.5076 | 44229.508 | 44229.5083 | 44229.5087 | 44229.509 | 44229.5094 | 44229.5097 | 44229.5101 | 44229.5104 | 44229.5108 | 44229.5111 | 44229.5115 | 44229.5118 | 44229.5122 | 44229.5125 | 44229.5128 | 44229.5132 | 44229.5135 | 44229.5139 | 44229.5142 | 44229.5146 | 44229.5149 | 44229.5153 | 44229.5156 | 44229.516 | 44229.5163 | 44229.5167 | 44229.517 | 44229.5174 | 44229.5177 | 44229.5181 | 44229.5184 | 44229.5188 | 44229.5191 | 44229.5194 | 44229.5198 | 44229.5201 | 44229.5205 | 44229.5208 | 44229.5212 | 44229.5215 | 44229.5219 | 44229.5222 | 44229.5226 | 44229.5229 | 44229.5233 | 44229.5236 | 44229.524 | 44229.5243 | 44229.5247 | 44229.525 | 44229.5253 | 44229.5257 | 44229.526 | 44229.5264 | 44229.5267 | 44229.5271 | 44229.5274 | 44229.5278 | 44229.5281 | 44229.5285 | 44229.5288 | 44229.5292 | 44229.5295 | 44229.5299 | 44229.5302 | 44229.5306 | 44229.5309 | 44229.5313 | 44229.5316 | 44229.5319 | 44229.5323 | 44229.5326 | 44229.533
| Wake Up | 44229.2917 | 44229.3021
| Start Coffee Maker | 44229.3021 | 44229.3056
| Have Shower | 44229.3056 | 44229.3125
| Get Dressed | 44229.3125 | 44229.316
| Make Toast | 44229.316 | 44229.3194
| Pour Coffee | 44229.316 | 44229.3174
| Add Milk | 44229.3174 | 44229.3177
| Eat Breakfast | 44229.3194 | 44229.3368
| Watch News | 44229.316 | 44229.3576
| Begin Work | 44229.3576 | 44229.691
| Make Dinner | 44229.691 | 44229.7118
| Eat Dinner | 44229.7118 | 44229.7326
| Create Gantt Chart | 44229.7326 | 44229.7743
| Sleep | 44229.7743 | 44230.066